## Portfolio Dashboard
Project | Name | Status | % Complete | Overdue Milestones | Open Risks | Highest Risk Score
P01 | AR Onboarding Module — Pilot | on_track | 35 | 0 | 1 | 2
P02 | VR Safety Training Simulation | at_risk | 40 | 1 | 2 | 9
P03 | AI Tutoring Chatbot — Co-Creation Pilot | on_track | 25 | 0 | 1 | 3
P04 | Immersive Product Training Library | delayed | 60 | 1 | 0 | 0
P05 | Micro-Learning Content Refresh | completed | 100 | 0 | 0 | 0

## Risk Log
Risk ID | Project | Description | Likelihood | Impact | Status | Owner
R01 | P02 | VR headset procurement delayed by vendor lead time | high | high | open | S. Hiremath
R02 | P02 | Two pilot sites have limited WiFi bandwidth for streaming content | medium | medium | open | S. Hiremath
R03 | P04 | Legacy content format incompatible with new player, requires manual conversion | high | medium | mitigated | S. Hiremath
R04 | P01 | AR prototype dependent on a third-party SDK update timeline | medium | low | open | S. Hiremath
R05 | P03 | Chatbot pilot requires legal review of training-data sourcing | low | high | open | S. Hiremath
R06 | P05 | Content refresh timeline overlapped with a public holiday week | low | low | closed | S. Hiremath

## Status Reports
Report ID | Project | Date | Summary | % Complete
SR01 | P01 | 2026-06-01 | Storyboard approved on schedule. AR prototype build underway. | 35
SR02 | P02 | 2026-06-01 | Scripting complete but hardware procurement is delayed; flagged as at-risk. | 40
SR03 | P03 | 2026-06-15 | Co-creation workshop completed with strong stakeholder engagement. | 25
SR04 | P04 | 2026-05-01 | Content migration behind schedule due to format-conversion effort. | 60
SR05 | P05 | 2026-07-10 | Rollout completed on schedule, no open issues. | 100